## Sheet1
Week | Date | Milestone | Status
1 | 2020-05-27 | IT project plan Wireframe mockup/Storyboard Create an HTML5 document for landing page | done
2 | 2020-06-03 | logo design images selection & design finalize theme/site color/font formats Update & create HTML5 documents for landing page/subpages Preview web pages on different devices Render features with CSS Markup/CSS validation | done
3 | 2020-06-10 | Render features with CSS Add slideshows/scrolling images on landing page Add magnifying effect to images on menu page Add contact form on contact page Markup/CSS validation | done
4 | 2020-06-17 | Render "order" page's features with JavaScript | done
5 | 2020-06-20 | Adjust the layout of "online order" function Add Googld Map to "contact" page Add popup window to "submit" button on "contact page" Upgrade to responsive footer Markup/CSS validation Website goes live | done